## Report
Test Report
Project Name |  | GSP24SE27
Project Code |  | SP24SE082
Test Environment Setup Description |  | Source Code
No | Function Group | Description | Total TCs | Passed | Failed | Untested | Pending | % TCs | % TCs | % TCs
1 | Unauthenticated User | Unauthenticated User can log into the system using these function | 8 | 8 | 0 | 0 | 0 | 100% | 100% | 0%
2 | Kichen Managaer | Admin can log into the system to use these function | 20 | 20 | 0 | 0 | 0 | 100% | 100% | 0%
3 | Authenticated Member | Member can log into the system to use these function | 34 | 34 | 0 | 0 | 0 | 100% | 100% | 0%
4 | Deliverer | Member can log into the system to use these function | 5 | 5 | 0 | 0 | 0 | 100% | 100% | 0%
5 | Admin | Member can log into the system to use these function | 7 | 7 | 0 | 0 | 0 | 100% | 100% | 0%

## Unauthenticated User
Test suit | Unauthenticated User
Created By | Nguyễn Huỳnh Phi
Created Date | 2024-04-21 |  | Review By | Nguyễn Hoài Phương
Task | Test By | Total TCs | TCs Passed | TCs Failed | TCs Untested | TCs Pending
1st Run | Nguyễn Huỳnh Phi | 8 | 8 | 0 | 0 | 0
Test case ID | Test Case | Test Case Description | Pre-Condition | Test Case Procedure | Expected Result | Passed/Failed | Date | Note
UnauthenticatedUser-01 | Check UI interface |  |  |  | System show onboarding screen and welcome screen | Pass | 2024-04-21
UnauthenticatedUser-02 | Unauthorized User want to login |  |  | 1. Click on "Đăng nhập" button. | The system will not login and have message text "Tài khoản hoặc mật khẩu không đúng" | Pass | 2024-04-21
UnauthenticatedUser-03 | Login | User login with account created on customer app | User already has an account | 1. User filling in information in "Số điện thoại" text box and "Mật khẩu" text box, Click "Đăng nhập" | System redirect Member to Home Page | Pass | 2024-04-21 | Account login: 0812345678 Password: Ab123456
UnauthenticatedUser-04 | Register | User create account on customer app | User not using their phone to create account | 1. User filling in information in "Số điện thoại" text box, "Mật khẩu" text box and "Xác nhận mật khẩu" text box, checked on "Chấp nhận điều với điều khoản" check box, Click "Đăng kí" | System redirect User to OTP confirmation screen | Pass | 2024-04-21 | Account register: 0966324249
UnauthenticatedUser-05 | OTP confirmation | User fill 6 number OTP on fill, OTP will be send to user by phone number |  | 1. User filling in 6 number of OTP getted from phone messaget to the text box, Click "Xác nhận OTP" | System notifiy success and redirect User to Login screen | Pass | 2024-04-21 | Account register: 0966324249
UnauthenticatedUser-06 | Login | Kichen manager login on kichen website | User already has an account | 1. User filling in information in "Tên đăng nhập" text box and "Mật khẩu" text box, Click "Đăng nhập" | System redirect Kichen manager to Kichen Page | Pass | 2024-04-21 | Account login: kitchen.manager01.beanfast@gmail.com Password: 12345678
UnauthenticatedUser-07 | Login | Deliver login on delivery app | User already has an account | 1. User filling in information in "Tên đăng nhập" text box and "Mật khẩu" text box, Click "Đăng nhập" | System redirect Deliverer to Deliver Page | Pass | 2024-04-21 | Account login: deliverer01.beanfast@gmail.com Password: 12345678
UnauthenticatedUser-08 | Login | Admin login on admin website | User already has an account | 1. User filling in information in "Tên đăng nhập" text box and "Mật khẩu" text box, Click "Đăng nhập" | System redirect Admin to Admin Page | Pass | 2024-04-21 | Account login: admin01.beanfast@gmail.com Password: 12345678

## Authenticated Member
Test suit | Member
Created By | Nguyễn Huỳnh Phi
Created Date | 2024-04-21 |  | Review By | Nguyễn Hoài Phương
Task | Test By | Total TCs | TCs Passed | TCs Failed | TCs Untested | TCs Pending
1st Run | Nguyễn Huỳnh Phi | 34 | 34 | 0 | 0 | 0
Test case ID | Test Case | Test Case Description | Pre-Condition | Test Case Procedure | Expected Result | Passed/Failed | Date | Note
Manage Children Profile
Member-01 | View list of children | Check UX/UI | Member already have a list of children depend | 1. Click "User" icon on bottom navbar 2. Click on "Danh sách học sinh" | System show list of children | Pass | 2024-04-21
Member-02 | View child detail information | Check UX/UI | Member already have a list of children depend | 1. Click "User" icon on bottom navbar 2. Click on "Danh sách học sinh" 3. Click "Child" row on list of children | System show detailed information of child | Pass | 2024-04-21
Member-03 | Create child profile | Input data |  | 1. Click "User" icon on bottom navbar 2. Click on "Danh sách học sinh" 3. Click on "Thêm học sinh" 4. Fill information of child "Họ và tên" text box , "Biệt danh" text box, select radio button "Giới tính" of child, pick day of brith of child, input "Chiều cao" and "Cân nặng" text box, select "Trường học" on "Chọn trường học" button, input "Lớp học" text box, upload image 5. Click on "Lưu thông tin" button |  | Pass | 2024-04-21
Member-04 | Change default children profile | Check UX/UI | Member already have a list of children depend | 1. Click "Child Profile" row on top of home page 2. Click on "Child" want to change in list of children | System show home page with update to a new choisen child | Pass | 2024-04-21
Member-05 | Update child profile | Input data | Member already have a list of children depend | 1. Click "User" icon on bottom navbar 2. Click on "Danh sách học sinh" 3. Click on "Edit" icon 4. Fill information of child "Họ và tên" text box , "Biệt danh" text box, select radio button "Giới tính" of child, pick day of brith of child, input "Chiều cao" and "Cân nặng" text box, select "Trường học" on "Chọn trường học" button, input "Lớp học" text box, update new Image. 5. Click on "Lưu thông tin" button |  | Pass | 2024-04-21
Member-06 | View QR code | Check UX/UI |  | 1. Click "QR icon" on bottom navbar | System show QR and update after 60 second | Pass | 2024-04-21
Member-07 | Generate QR code | Generate QR code |  | 1. Click "QR icon" on bottom navbar 2. Click on "Cập nhật" button | System show new QR and update after 60 second | Pass | 2024-04-21
Manage booking action
Member-08 | View list food by child school | Check UX/UI | Have a menu of food that member chosen | 1. Select child want to booking for 2. Select on date on date table 3. Select session want to pick up | System show list of food | Pass | 2024-04-21
Member-09 | View food detail | Check UX/UI |  | 1. Click on food row | System show food detail | Pass | 2024-04-21
Member-10 | View cart detail | Check UX/UI | Have item in cart | 1. Click on shopping cart icon on the appbar | System show list of food has been added | Pass | 2024-04-21
Member-11 | Manage cart of children | Input data | Have item in cart | 1. Select the child you want to book 2. Select a date on the date panel 3. Select pickup time session 4. Add food to cart in desired quantity 5. Click the shopping cart icon on the application bar 6. Change the item quantity | System show list of food has been added and amount of them | Pass | 2024-04-21
Member-12 | View confirmation order | Check UX/UI | Have item in cart | 1. Click on cart icon on appbar 2. Change amount of item 3. Click on "Đặt hàng" button | System show screen of order confirmation for member to review | Pass | 2024-04-21
Member-13 | Change pickup school gate | Edit data | In confirmation order page | 1. Click on cart icon on appbar 2. Change amount of item 3. Click on "Đặt hàng" button 4. Click on "edit" icon button 5. Select pickup desired location on bottom dialog | System update to a new location on order confirmation screen | Pass | 2024-04-21
Member-14 | Booking food | Input data | Member have enough money to booking order | 1. Select the child you want to book 2. Select a date on the date panel 3. Select pickup time session 4. Add food to cart in desired quantity 5. Click the shopping cart icon on the application bar 6. Click on "Đặt hàng" button, on cart page 7. Click Click on "Đặt hàng" button on confirm order page | System show the success message and forward to order screen | Pass | 2024-04-21
Member-15 | View order by status | Check UX/UI |  | 1. Click on "Order" icon on bottom navbar 2. Select order status | System show list of order by status | Pass | 2024-04-21
Member-16 | View order detail | Check UX/UI | The Menber has placed a food order | 1. Click on order | System show order detail | Pass | 2024-04-21
Manage deposit
Member-17 | View amount money on wallet | Check UX/UI |  | 1. Click on eye icon | System show amount of money in wallet | Pass | 2024-04-21
Member-18 | Add money to wallet | Input data |  | 1. Click on "Nạp thêm" button 2. Select or input amount desired to exchange 3. Click on "Nạp thêm" button 4. Fill on bank account information 5. Fill OTP of bank | System show success message and forward to home page | Pass | 2024-04-21
Member-19 | View money transaction | Check UX/UI |  | 1. Click on "Transaction" icon on bottom navbar | System show list of money transaction by month | Pass | 2024-04-21
Manage point
Member-20 | View point wallet | Check UX/UI |  | 1. Click on "Đổi quà" button 2. Select child desired to view | System show point on the top right of screen | Pass | 2024-04-21
Member-21 | View point transaction | Check UX/UI |  | 1. Click on "Đổi quà" button 2. Select child desired to view 3. Select tab "Tích điểm/ Dùng điểm" | System show list of point transaction by month | Pass | 2024-04-21
Gift exchange
Member-22 | View list of gift | Check UX/UI | Have children depended on | 1. Click on "Đổi quà" button | System show list of gift for child to exchange | Pass | 2024-04-21
Member-23 | View gift exchange detail | Check UX/UI | Have children depended on | 1. Click on "Đổi quà" button 2. Click on "Gift" row | System show gift detail information | Pass | 2024-04-21
Member-24 | Exchange gift |  | Member have enough gift point to booking gift order | 1. Select child desired to exchange gift 2. Click on "Đổi quà" button 3. Slecet on "Đổi quà" button to select the gift desired to exchange 4. Select date to pickup 5. Select time to pickup 6. Select "Đặt hàng" button | System show the success message and forward to "Lịch sử đổi quà" screen | Pass | 2024-04-21
Member-25 | View confirmation exchange | Check UX/UI | Menber select correct date and time to pickup | 1. Select child desired to exchange gift 1. Click on "Đổi quà" button 2. Slecet on "Đổi quà" button to select the gift desired to exchange 3. Select date to pickup 4. Select time to pickup | System show screen of gift order confirmation for member to review | Pass | 2024-04-21
Member-26 | Change pickup location on confirmation exchange | Change data |  | 1. Select child desired to exchange gift 1. Click on "Đổi quà" button 2. Slecet on "Đổi quà" button to select the gift desired to exchange 3. Select date to pickup 4. Select time to pickup 5. Update location to pickup when click on "edit" icon button | System update to a new location on gift order confirmation screen | Pass | 2024-04-21
Member-27 | Change time to pickup on confirmation exchange | Change data |  | 1. Select child desired to exchange gift 1. Click on "Đổi quà" button 2. Slecet on "Đổi quà" button to select the gift desired to exchange 3. Select date to pickup 4. Select time to pickup 5. Update time to pickup when click on "edit" icon button | System update to a new time on gift order confirmation screen | Pass | 2024-04-21
Member-28 | View order exchange gift | Check UX/UI | The Menber has placed a gift order | 1. Click on "Đổi quà" buttom 2. Select tab "Lịch sử đổi thưởng" | System show list of gift order on "Lịch sử đổi quà" tab | Pass | 2024-04-21
Play game
Member-29 | View list game | Check UX/UI |  | 1. Click on "Trò chơi" button | System show list of game | Pass | 2024-04-21
Member-30 | View number of plays avaible | Check UX/UI |  | 1. Click on "Trò chơi" button | System show number of plays remaining | Pass | 2024-04-21
Member-31 | Play game | Game play | Child's number of plays remaining more than 0 | 1. Click on "Trò chơi" button 2. Select child desired to play 3. Click on game desired to play | System show game play | Pass | 2024-04-21
Notification
Member-32 | View list of notification | Check UX/UI |  | 1. Click on "Notification" icon button | System show list of notification | Pass | 2024-04-21
Manage Profile
Member-33 | View detailed information member | Check UX/UI |  | 1. Click "User" icon on Navbar 2. Click on "Trang cá nhân" | System show member information | Pass | 2024-04-21
Member-34 | Update member menber name | Input data |  | 1. Click "User" icon on Navbar 2. Click on "Trang cá nhân" 3. Click "Edit" icon on name row 4. Fill new name of member | System update member name | Pass | 2024-04-22

## Kichen Manager
Test suit | KitchenManager
Created By | Nguyễn Huỳnh Phi
Created Date | 2024-04-22 |  | Review By | Nguyễn Hoài Phương
Task | Test By | Total TCs | TCs Passed | TCs Failed | TCs Untested | TCs Pending
1st Run | Nguyễn Huỳnh Phi | 20 | 20 | 0 | 0 | 0
Test case ID | Test Case | Test Case Description | Pre-Condition | Test Case Procedure | Expected Result | Passed/Failed | Date | Note
Dashboard
KichenManager-01 | View Dashboard | Check UI/UX |  | 1. Click on dashboard icon on tabbar | System show list of dashboard | Pass | 2024-04-22
Menu management
KichenManager-02 | View menu list | Check UI/UX |  | 1. Click on menu icon | System show list of menu | Pass | 2024-04-22
KichenManager-03 | Create menu | Input data |  | 1. Click on menu icon 2. Click on button 'Thêm' 3. Fill in information of menu 4. Click on "Tạo" button | System notify add sucsess and forward to menu list screen | Pass | 2024-04-22
Food management
KichenManager-04 | View food list | Check UI/UX |  | 1. Click on food icon | System show list of food | Pass | 2024-04-22
KichenManager-05 | Create food | Input data |  | 1. Click on food icon 2. Click on button 'Thêm' 3. Fill in information of food 4. Click on "Tạo" button | System notify add sucsess and forward to food list screen | Pass | 2024-04-22
KichenManager-06 | View Food detail | Check UI/UX |  | 1. Click on food icon 2. Click on detail icon | System show food detail | Pass | 2024-04-22
KichenManager-07 | Search food | Input data |  | 1. Fill in name of food | System show list of food base on name | Pass | 2024-04-22
Order Management
KichenManager-08 | View order list | Check UI/UX |  | 1. Click on order icon | System show list of order | Pass | 2024-04-22
KichenManager-09 | View order detail | Check UI/UX |  | 1. Click on order icon 2. Click on detail icon | System show order detail | Pass | 2024-04-22
KichenManager-10 | Update order status | Update data |  | 1. Click on order icon 2. Click on delete icon | System notify udpate sucsess and status change into "Đã huỷ" | Pass | 2024-04-22
Gift Management
KichenManager-11 | View gift list | Check UI/UX |  | 1. Click on gift icon | System show list of gift | Pass | 2024-04-22
KichenManager-12 | Create gift | Input data |  | 1. Click on gift icon 2. Click on button 'Thêm' 3. Fill in information of gift 4. Click on "Tạo" button | System notify add sucsess and forward to gift list screen | Pass | 2024-04-22
KichenManager-13 | View gift detail | Check UI/UX |  | 1. Click on gift icon 2. Click on detail icon | System show gift detail | Pass | 2024-04-22
KichenManager-14 | Search gift | Input data |  | 1. Fill in name of gift | System show list of gift base on name | Pass | 2024-04-22
School Management
KichenManager-15 | View school list | Check UI/UX |  | 1. Click on school icon | System show list of school | Pass | 2024-04-22
KichenManager-16 | Create school | Input data |  | 1. Click on school icon 2. Click on button 'Thêm' 3. Fill in information of school 4. Click on "Tạo" button | System notify add sucsess and forward to school list screen | Pass | 2024-04-22
KichenManager-17 | View school detail | Check UI/UX |  | 1. Click on school icon 2. Click on detail icon | System show school detail | Pass | 2024-04-22
Session Management
KichenManager-18 | Create session | Input data |  | 1. Click on school icon 2. Select on school desired to view list of session 3. Click on "Thêm" button 4. Select menu desired to add in session 5. Input session time detail 6. Select school gate and deliverer default for each gate of school | System notify add sucsess | Pass | 2024-04-22
KichenManager-19 | View session list | Check UI/UX |  | 1. Click on school icon 2. Select on school desired to view list of session | System show list of session | Pass | 2024-04-22
KichenManager-20 | View session detail | Check UI/UX |  | 1. Click on school icon 2. Select on school desired to view list of session 3. Select on session row desired to view detail | System show session detail | Pass | 2024-04-22

## Deliverer
Test suit | Deliverer
Created By | Nguyễn Huỳnh Phi
Created Date | 2024-04-22 |  | Review By | Nguyễn Hoài Phương
Task | Test By | Total TCs | TCs Passed | TCs Failed | TCs Untested | TCs Pending
1st Run | Nguyễn Huỳnh Phi | 5 | 5 | 0 | 0 | 0
Test case ID | Test Case | Test Case Description | Pre-Condition | Test Case Procedure | Expected Result | Passed/Failed | Date | Note
Manager Category
Deliverer-01 | View Deliverery schedules | Check UI/UX |  | 1. Click on icon Deliverery schedules | System show a list of Deliverery schedules | Pass | 2024-04-22
Deliverer-02 | View list of orders waiting for delivery | Check UI/UX | Deliverer have a list of orders waiting for delivery | 1. Click on icon order | System show a list of orders waiting for delivery | Pass | 2024-04-22
Deliverer-03 | View order detail | Check UI/UX | Deliverer have order waiting for delivery | 1. Click on icon order 2. Select order desired to view | System show a order detail | Pass | 2024-04-22
Deliverer-04 | Update food order status | Change status |  | 1. Click on icon food order 2. Click on food order detail 3. Click on update "Cập nhật trạng thái" | System notify udpate sucsess and status | Pass | 2024-04-22
Deliverer-05 | Update gift order status | Change status |  | 1. Click on icon gift order 2. Click on gift order detail 3. Click on update "Cập nhật trạng thái" | System notify udpate sucsess and status | Pass | 2024-04-22

## Admin
Test suit | Admin
Created By | Nguyễn Huỳnh Phi
Created Date | 2024-04-22 |  | Review By | Nguyễn Hoài Phương
Task | Test By | Total TCs | TCs Passed | TCs Failed | TCs Untested | TCs Pending
1st Run | Nguyễn Huỳnh Phi | 7 | 7 | 0 | 0 | 0
Test case ID | Test Case | Test Case Description | Pre-Condition | Test Case Procedure | Expected Result | Passed/Failed | Date | Note
Manager Category
Admin-01 | View list of user | Check UI/UX |  | 1. Click on user icon | System show a list of user | Pass | 2024-04-22
Admin-02 | Create kitchen manager account | Input data |  | 1. Click on "Thêm" button 2. Fill information of account 3. Select kitchen place kitchen manager management 4. Click "Tạo" button | System notify add sucsess and forward to user list screen | Pass | 2024-04-22
Admin-03 | Create deliverer manager account | Input data |  | 1. Click on "Thêm" button 2. Fill information of account 3. Click "Tạo" button | System notify add sucsess and forward to user list screen | Pass | 2024-04-22
Admin-04 | Ban account | Update data |  | 1. Click on user icon 2. Click on ban icon | System notify udpate sucsess and status change into "ban" | Pass | 2024-04-22
Kitchen Management
Admin-05 | View kitchen list | Check UI/UX |  | 1. Click on kitchen icon | System show list of kitchen | Pass | 2024-04-22
Admin-06 | Create kitchen | Input data |  | 1. Click on kitchen icon 2. Click on button 'Thêm' 3. Fill in information of kitchen 4. Click on "Tạo" button | System notify add sucsess and forward to kitchen list screen | Pass | 2024-04-22
Admin-07 | View kitchen detail | Check UI/UX |  | 1. Click on kitchen icon 2. Click on detail icon | System show kitchen detail | Pass | 2024-04-22